## Overview
Item | Value
Project Name | Human Resource Information System (HRIS)
Client | PT Bintang Fajar Persada
Version | 1.0
Platform | Web Admin, Android, iOS
Methodology | Agile Scrum
Estimated Duration | xx Weeks
Warranty | 3 Months
Status | Requirement Gathering

## Modul
No | Modul | Sub Modul | Feature | Role | Web | Mobile (Andro & IOS) | PIC Pengerjaan | Man-Days - Web | Man-Days - Mobile | Remarks | Column 1
1 | Authentication | Login | • Email Login • Remember Me • Multi Company Login | Super Admin, HR, Manager, Employee, Finance, Director | TRUE | TRUE | Bagus | 2 | 3 |  | bagus = 80 hanif = 80 nanang = 80
2 | Authentication | Account Activation | • First Login Activation • Email Activation • Force Change Password | Super Admin, HR, Employee | TRUE | TRUE | Bagus | 2 | 2
3 | Authentication | Password Management | • Forgot Password • Change Password • Reset Password (HR) | Super Admin, HR, Employee | TRUE | TRUE | Bagus | 2 | 2
4 | Authentication | Device Management | • Register Device • Registered Device Information • Request Change Device • Device Login History • Device Binding (Regist, Request Changes, Approval Request & Changes) | Super Admin, HR, Employee | TRUE | TRUE | Hanif | 2 | 2
5 | Authentication | Session | • Session Management • Logout | Semua Role | TRUE | TRUE | Hanif | 2 | 2
6 | Dashboard | Dashboard | • HR Dashboard • Employee Dashboard • Manager Dashboard • Executive Dashboard | Super Admin, HR, Manager, Employee, Finance, Director | TRUE | TRUE | Nanang | 3 | 3
7 | Dashboard | Widget | • KPI Summary • Attendance Summary • Leave Summary • Payroll Summary • Announcement • Calendar • Employee Birthday • New Employee | Super Admin, HR, Manager | TRUE | TRUE | Nanang | 3 | 3
8 | Employee Management | Employee Information | • Employee Profile • Personal Information • Employment Information • Employee Status • Employee Photo • Bank Account • NPWP • BPJS Number | Super Admin, HR | TRUE | TRUE | Hanif | 3 | 3 | Mobile: View & Edit Profile
9 | Employee Management | Organization | • Organization Structure • Division • Department • Position | Super Admin, HR | TRUE | TRUE | Hanif | 2 | 2 | Mobile: View only
10 | Employee Management | Employment | • Employment Contract • Employment History • Mutation • Promotion • Resignation | Super Admin, HR | TRUE | FALSE | Nanang | 3 | 3
11 | Employee Management | Document | • Employee Document • Certificate • Attachment | Super Admin, HR | TRUE | FALSE | Nanang | 3 | 3
12 | Attendance | Attendance | • Check In • Check Out • Attendance History • Request Attendance (Forgot Check In/Out) • Attendance Approval • Attendance Recap • Late Attendance • Early Leave • Auto Check Out • Manual Attendance (HR) • WFO • WFH • Hybrid Working/WFA | HR, Manager, Employee | TRUE | TRUE | Bagus | 7 | 7 | Include 2 opsi: - penyimpanan absensi Foto dengan retensi data yang ditentukan - penyimpanan absensi menggunakan similarity (percentage) - terdapat setting bisa absen dimanapun (tidak ada zona merah) - terdapat setting hanya bisa absen diwilayah kantor/wilayah tertantu (diatur based on titik koordinat)
13 | Attendance | Shift Management | • Shift Schedule • Shift Assignment • Shift Swap • Working Calendar | Super Admin, HR | TRUE | FALSE | Hanif | 3 | 4
14 | Attendance | Face Recognition | • Face Enrollment • Face Verification • Face Matching • Liveness Detection • Blink Detection • Head Movement Detection (Look Left & Right) • Face Quality Validation • Face Reset | HR, Employee | TRUE | TRUE | Bagus | 4 | 4 | Web: Reset/Management
15 | Attendance | GPS Security | • Geofence • Fake GPS Detection • Mock Location Detection • Root Detection • Jailbreak Detection • GPS Accuracy Validation • Suspicious Location Detection | Super Admin, HR | TRUE | TRUE | Nanang | 4 | 4 | Web: Configuration
16 | Leave Management | Leave | • Leave Request • Leave Approval • Leave Balance• Leave History | HR, Manager, Employee | TRUE | TRUE | Nanang | 7 | 7
17 | Overtime | Overtime | • Overtime Request • Overtime Approval • Overtime Calculation • Overtime History | HR, Manager, Employee | TRUE | TRUE | Hanif | 7 | 7
18 | Claim | Reimbursement | • Claim Request • Claim Approval • Claim History | HR, Manager, Employee | TRUE | TRUE | Bagus | 3 | 4
19 | Business Trip | Official Travel | • Business Trip Request • Business Trip Approval • Business Trip History | HR, Manager, Employee | TRUE | TRUE | Bagus | 3 | 4
20 | Time Management | Time Tracker | • Time Tracker • Working Time Report | HR, Employee | TRUE | TRUE | Hanif | 3 | 3
21 | Time Management | Daily Report | • Daily Activity • Daily Progress Report | HR, Employee | TRUE | TRUE | Hanif | 3 | 3
22 | Employee Self Service | Employee Services | • Employee Profile • Attendance • Leave • Overtime • Claim • Business Trip • Payslip • Announcement | Employee | FALSE | TRUE | Hanif | 3 | 4
23 | Payroll | Payroll Management | • Payroll Configuration • Salary Component • Payroll Process • Payroll History • Salary Adjustment • THR • Bonus • Incentive | Super Admin, HR, Finance | TRUE | FALSE | Bagus | 7 | 7
24 | Payroll | Tax | • PPh21 Calculation • PTKP Configuration • TER Configuration | Finance | TRUE | TRUE | Nanang | 4 | 4 | Mobile: view only no NPWP di Profile, cukup 1 page dengan informasi BPJS
25 | Payroll | BPJS | • BPJS Kesehatan • BPJS Ketenagakerjaan | Finance | TRUE | TRUE | Nanang | 4 | 4 | Mobile: view only no BPJS di Profile, cukup 1 page dengan informasi NPWP
26 | Payroll | Payslip | • View Payslip • Download Payslip | Employee | TRUE | TRUE | Nanang | 4 | 4
27 | Reporting | Dashboard | • HR Dashboard • Executive Dashboard | Super Admin, HR, Finance, Director | TRUE | FALSE | Bagus | 2 | 2
28 | Reporting | Report | • Attendance Report • Payroll Report • Leave Report • Employee Report • Overtime Report | HR, Finance, Director | TRUE | TRUE | Bagus | 2 | 2 | Mobile: Personal Report
29 | Reporting | Export | • Export Excel • Export PDF | HR, Finance | TRUE | FALSE | Bagus | 2 | 2
30 | Settings | Company | • Company Profile • Branch • Office Location | Super Admin | TRUE | FALSE | Hanif | 3 | 3
31 | Settings | User Management | • User Management • Role & Permission | Super Admin | TRUE | FALSE | Hanif | 3 | 3
32 | Settings | Master Data | • Department • Division • Position • Grade • Shift • Holiday • Leave Type • Payroll Component | Super Admin | TRUE | FALSE | Nanang | 3 | 3
33 | Settings | Approval Workflow | • Approval Matrix • Multi Level Approval | Super Admin | TRUE | FALSE | Nanang | 2 | 2
34 | Settings | Notification | • Email Notification • Push Notification | Super Admin | TRUE | TRUE | Hanif | 3 | 3
35 | Integration | Integration | • REST API • Email Integration | Super Admin | TRUE | FALSE | Hanif | 2 | 2
36 | Security | Audit & Security | • Audit Trail • Login History • Activity Log • Password Policy | Super Admin | TRUE | FALSE | Bagus | 2 | 2
37 | Security | Device Security | • Device Approval • Device Reset • Device Replacement • Registered Device List | Super Admin, HR | TRUE | TRUE | Bagus | 2 | 2 | Mobile: Request Device Changes
38 | config | config | • Setting VPS, Infra, deployment |  | TRUE | TRUE | Bagus | 2 | 2
[5 empty] | FALSE | FALSE |  | 121 | 126
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE
[5 empty] | FALSE | FALSE

## Tech Stack
No | Component | Layer | Technology | Library/Framework | Remarks | Price (if any)
1 | Backend | Language | Go | Go 1.24+ | Performa tinggi, concurrency ringan
2 | Backend | HTTP Framework | Gin | gin-gonic/gin | Mature, cepat, middleware lengkap
3 | Backend | Query Builder | Squirrel | Masterminds/squirrel | SQL dinamis, ringan, mudah dibaca
4 | Backend | Database Driver | pgx | jackc/pgx/v5 | Driver PostgreSQL berperforma tinggi
5 | Backend | Migration | golang-migrate | golang-migrate/migrate | Standar migrasi database
6 | Backend | Authentication | JWT | golang-jwt/jwt/v5 | Access & Refresh Token
7 | Backend | Password Hashing | Argon2id | golang.org/x/crypto | Lebih modern dibanding bcrypt
8 | Backend | Validation | validator | go-playground/validator/v10 | Validasi struct
9 | Backend | Configuration | Viper | spf13/viper | Multi environment configuration
10 | Backend | Logging | Zap | uber-go/zap | Structured logging
11 | Backend | API Documentation | Swagger | swaggo/swag | Generate dokumentasi otomatis
12 | Backend | Dependency Injection | Wire | google/wire | Compile-time Dependency Injection
13 | Backend | Background Queue | RabbitMQ | amqp091-go | Email, payroll, report, notification
14 | Backend | Scheduler | robfig/cron | robfig/cron/v3 | Cron job
15 | Backend | Cache | Redis | redis/go-redis/v9 | Session & cache
16 | Backend | File Storage | MinIO | minio-go/v7 | S3-compatible Object Storage
17 | Backend | Email | SMTP | gomail | Email notifikasi
18 | Backend | Testing | Testify | stretchr/testify | Unit & integration testing
19 | Front End | Framework | React 19 | React
20 | Front End | Build Tool | Vite | Vite
21 | Front End | Language | TypeScript | TypeScript
22 | Front End | Routing | TanStack Router | @tanstack/react-router
23 | Front End | State Management | Zustand | Zustand
24 | Front End | Server State | TanStack Query | @tanstack/react-query
25 | Front End | UI Component | shadcn/ui | Radix UI
26 | Front End | CSS | Tailwind CSS | Tailwind CSS
27 | Front End | Form | React Hook Form | react-hook-form
28 | Front End | Validation | Zod | zod
29 | Front End | Table | TanStack Table | @tanstack/react-table
30 | Front End | Charts | Apache ECharts | echarts-for-react
31 | Front End | HTTP Client | Axios | Axios
32 | Front End | Date | Day.js | Day.js
33 | Front End | Testing | Vitest | Vitest + React Testing Library
34 | Mobile | Push Notification | Firebase FCM |  | Android Free, IOS any cost | ± Rp1,6–2 juta/tahun (Apple)
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## User Roles
Role | Description | Main Access | Remarks
Super Admin | Konfigurasi sistem | Full Access
HR Admin | Operasional HR | Employee, Attendance, Payroll
Manager | Approval | Approval, Team Dashboard
Employee | Employee Self Service | Attendance, Leave, Claim, etc
Finance | Payroll | Payroll, Tax, BPJS
Director | Executive Dashboard | Dashboard & Reporting

## Assumptions
No | Assumption | Remarks | Column 4
1 | Payroll formula disediakan oleh client.
2 | Pajak PPh21 mengikuti regulasi yang berlaku.
3 | BPJS mengikuti kebijakan perusahaan.
4 | Face Recognition menggunakan teknologi AI dengan liveness detection.
5 | Fake GPS, Mock Location, Root/Jailbreak Detection diterapkan sebagai mekanisme mitigasi kecurangan.
6 | Integrasi pihak ketiga (ERP, Accounting, Fingerprint, WhatsApp, dll.) di luar scope kecuali disepakati.
7 | Semua perubahan requirement setelah approval akan diproses melalui Change Request (CR).

## Project Activity
Phase | PM & Analyst | Backend Developer | Frontend Web | Mobile Developer | QA / Tester
Initiation | Requirement Gathering Business Process Analysis Stakeholder Meeting | Technical Feasibility Analysis | UI Requirement Review | Mobile Requirement Review | Requirement Review
Planning | Project PlanningTimeline Sprint Planning | Database DesignAPI Architecture | Frontend Architecture | Mobile Architecture | Test Planning Test Strategy
Design | Design Review Client Approval | API Design Review | UI Implementation Review | Mobile UI Review | UI Validation
Development | Sprint Monitoring | API Development Business Logic Database Development | Web Module Development Integration API | Android/iOS Development Device Integration Face Recognition GPS Integration | Functional Testing Regression Testing Bug Reporting
Integration | Progress Monitoring | API Integration | Web Integration Testing | Mobile Integration Testing | API Testing Integration Testing
UAT | Client Coordination User Training | Bug Fixing | Bug Fixing | Bug Fixing | UAT Support Bug Verification
Deployment | Go Live Coordination | Production Deployment Server Configuration | Production Build | Android/iOS Release | Smoke Testing
Warranty / Support | Support MonitoringChange Request | Bug FixMinor Enhancement | Bug Fix | Bug Fix | Regression Testing Support Validation

## Cost Project
Resource | Qty | Man-Days (MD) | Duration (Month) | Total Cost (excl. Tax) | Total Cost (Incl. Tax) | Remarks
Resource
Project Manager, Analyst, Tester, Design UI/UX | 2 | 120 | 4 | 78000000 | 79950000
Web & MobileDeveloper | 3 | 260 | 4 | 156000000 | 159900000
Total Cost HRIS | 5 | 380 | 4 | 234000000 | 239850000
Infra Server (Detail)
App Server 1 | - | - | - | 213900 | 219247.5 | Harga promo dalam 2tahun
App Server 2 | - | - | - | 213900 | 219247.5 | Harga promo dalam 2tahun
Database | - | - | - | 426900 | 437572.5 | Harga promo dalam 2tahun
Infrastructure | - | - | - | 151900 | 155697.5 | Harga promo dalam 2tahun
Infrastruktur VPS | - | - | - | 12079200 | 12381180 | Harga di tahun pertama
Domain | - | - | - | 200000 | 205000 | Harga di tahun pertama
Apple Developer Program | - | - | - | 1700000 | 1742500 | Harga di tahun pertama
Push Notification - Firebase FCM | - | - | - | 2000000 | 2050000
Total Cost Infra Server | - | - | - | 16985800 | 17410445
Total Cost HRIS |  |  |  | 250985800 | 257260445
Notes:
*tax -> dihitung pajak perorangan yaitu 2,5% seperti prj sebelumnya. karena freelance

## Pricing Server
Server | Paket | Spesifikasi | Service | Harga Asli | Harga Promo (2 Tahun) | Harga Setelah 2 Tahun
App Server 1 | KVM 4 | 4 vCPU, 16 GB RAM, 200 GB NVMe | Nginx, Backend API, Worker | 679900 | 213900 | 465900
App Server 2 | KVM 4 | 4 vCPU, 16 GB RAM, 200 GB NVMe | Backend API, Worker | 679900 | 213900 | 465900
Database | KVM 8 | 8 vCPU, 32 GB RAM, 400 GB NVMe | PostgreSQL | 1203900 | 426900 | 853900
Infrastructure | KVM 2 | 2 vCPU, 8 GB RAM, 100 GB NVMe | Redis, RabbitMQ, MinIO, Prometheus, Grafana, Loki | 407900 | 151900 | 232900
TOTAL / Bulan |  |  |  | 2971600 | 1006600 | 2018600
https://www.hostinger.com/id/hosting-vps#pricing
Komponen | Tahun Pertama | Tahun Kedua | Tahun Ketiga dan Seterusnya
Infrastruktur VPS | Rp12.079.200 (Harga Promo) | Rp12.079.200 (Harga Promo) | Rp24.223.200 (Harga Normal)
Domain | ± Rp200.000 | ± Rp200.000 | ± Rp200.000
Apple Developer Program | ± Rp1.700.000 | ± Rp1.700.000 | ± Rp1.700.000
Total | ± Rp14.000.000 | ± Rp14.000.000
Total | ± Rp14,4 juta | ± Rp14 juta | ± Rp26.100.000
Layer | Technology | Library / Framework | Alasan
Language | Go | Go 1.24+ | Performa tinggi, concurrency ringan
HTTP Framework | Gin | gin-gonic/gin | Mature, cepat, middleware lengkap
Query Builder | Squirrel | Masterminds/squirrel | SQL dinamis, ringan, mudah dibaca
Database Driver | pgx | jackc/pgx/v5 | Driver PostgreSQL berperforma tinggi
Migration | golang-migrate | golang-migrate/migrate | Standar migrasi database
Authentication | JWT | golang-jwt/jwt/v5 | Access & Refresh Token
Password Hashing | Argon2id | golang.org/x/crypto | Lebih modern dibanding bcrypt
Validation | validator | go-playground/validator/v10 | Validasi struct
Configuration | Viper | spf13/viper | Multi environment configuration
Logging | Zap | uber-go/zap | Structured logging
API Documentation | Swagger | swaggo/swag | Generate dokumentasi otomatis
Dependency Injection | Wire | google/wire | Compile-time Dependency Injection
Background Queue | RabbitMQ | amqp091-go | Email, payroll, report, notification
Scheduler | robfig/cron | robfig/cron/v3 | Cron job
Cache | Redis | redis/go-redis/v9 | Session & cache
File Storage | MinIO | minio-go/v7 | S3-compatible Object Storage
Email | SMTP | gomail | Email notifikasi
Testing | Testify | stretchr/testify | Unit & integration testing
Layer | Technology | Library / Framework
Framework | React 19 | React
Build Tool | Vite | Vite
Language | TypeScript | TypeScript
Routing | TanStack Router | @tanstack/react-router
State Management | Zustand | Zustand
Server State | TanStack Query | @tanstack/react-query
UI Component | shadcn/ui | Radix UI
CSS | Tailwind CSS | Tailwind CSS
Form | React Hook Form | react-hook-form
Validation | Zod | zod
Table | TanStack Table | @tanstack/react-table
Charts | Apache ECharts | echarts-for-react
HTTP Client | Axios | Axios
Date | Day.js | Day.js
Testing | Vitest | Vitest + React Testing Library